## Table of Contents
TI Information - Selective Disclosure
Copyright (C) 2023 Texas Instruments Incorporated
Sheet No. | Title | Purpose
1 | Table of Contents | Provides an overview of the contents of the complete report.
2 | Script Input Parameters | Displays the input parameters provided to generate this report.
3 | Coverage Summary | Provides a summary report of Coverage for both Forward and Backward Traceability.
4 | Forward Traceability | Provides the detailed Forward Traceability Report from Marketing Requirements(MRD) to Software Product Specifications(SPS) & from Software Product Specifications(SPS) to Test Cases.
5 | Backward Traceability | Provides the detailed Backward Traceability Report from Software Product Specifications(SPS) to Marketing Requirements(MRD) & from Test Cases to Software Product Specifications(SPS).
6 | Traceability Deviations | Provides the details of all the Traceability Deviations.
7 | Revision History | Provides Template Revision History.

## Script Input Parameters
CM Record Key | Baseline Project Key | Report generated on
ISS-1160 | ISS | 2025-09-10 20:28:25.143213-05:00 CDT

## Coverage Summary
Forward Coverage Type | Forward Percentage Covered | Backward Coverage Type | Backward Percentage Covered
Marketing Requirement (MRD) -> Software Product Specification (SPS) | 100.0% | Software Product Specification (SPS) -> Marketing Requirement (MRD) | 100.0%
Software Product Specification (SPS) -> Test Case | 100.0% | Test Case -> Software Product Specification (SPS) | 100.0%

## Forward Traceability
MRD ID | SPS ID(s) | SPS ID | Test Case ID(s) | Test Case Scope
JACINTOREQ-7469 | ISS-588,ISS-600 | ISS-588 | ISS-753
SITREQ-4993 | ISS-588,ISS-600 | ISS-61 | ISS-90 | Integration
JACINTOREQ-236 | ISS-61,ISS-45,ISS-66,ISS-62,ISS-60,ISS-59,ISS-420 | ISS-944 | ISS-1128,ISS-1126,ISS-1129
JACINTOREQ-2887 | ISS-944,ISS-836,ISS-835,ISS-827,ISS-1088,ISS-830,ISS-832,ISS-943,ISS-1064,ISS-946,ISS-833,ISS-829,ISS-837,ISS-828,ISS-834,ISS-831 | ISS-817 | ISS-816
JACINTOREQ-3160 | ISS-944,ISS-836,ISS-835,ISS-827,ISS-1088,ISS-830,ISS-832,ISS-943,ISS-1064,ISS-946,ISS-833,ISS-829,ISS-837,ISS-828,ISS-834,ISS-831 | ISS-392 | ISS-300,ISS-297 | Unit,Unit
JACINTOREQ-592 | ISS-817 | ISS-731 | ISS-757,ISS-758
JACINTOREQ-310 | ISS-392,ISS-414,ISS-413,ISS-418,ISS-387,ISS-382 | ISS-400 | ISS-296 | Unit
JACINTOREQ-8281 | ISS-731 | ISS-132 | ISS-164 | Unit
JACINTOREQ-249 | ISS-400,ISS-375,ISS-402,ISS-399,ISS-379,ISS-395,ISS-384,ISS-389,ISS-398,ISS-376,ISS-380,ISS-403,ISS-401,ISS-385 | ISS-10 | ISS-65,ISS-1162,ISS-1161 | Integration,Integration,Integration
JACINTOREQ-438 | ISS-132,ISS-127,ISS-155,ISS-174,ISS-29,ISS-133,ISS-421 | ISS-777 | ISS-752
JACINTOREQ-303 | ISS-10,ISS-12,ISS-9,ISS-11,ISS-8 | ISS-80 | ISS-110 | Unit
JACINTOREQ-56 | ISS-10,ISS-12,ISS-9,ISS-11,ISS-128,ISS-8,ISS-124 | ISS-836 | ISS-1126,ISS-1129
JACINTOREQ-1049 | ISS-777,ISS-779,ISS-570,ISS-778 | ISS-841 | ISS-1128
JACINTOREQ-7520 | ISS-777 | ISS-416 | ISS-291 | Unit
JACINTOREQ-407 | ISS-80,ISS-79 | ISS-422 | ISS-303 | Unit
JACINTOREQ-2886 | ISS-841,ISS-838,ISS-839,ISS-1088,ISS-1064,ISS-840 | ISS-318 | ISS-303 | Unit
JACINTOREQ-3216 | ISS-841,ISS-838,ISS-839,ISS-1088,ISS-1064,ISS-840 | ISS-838 | ISS-1128
JACINTOREQ-528 | ISS-416,ISS-377,ISS-419,ISS-386,ISS-394,ISS-381 | ISS-568 | ISS-751
SITREQ-633 | ISS-416,ISS-422,ISS-414,ISS-417,ISS-413,ISS-418,ISS-419,ISS-415,ISS-412,ISS-423,ISS-420,ISS-421 | ISS-391 | ISS-752
JACINTOREQ-524 | ISS-422 | ISS-585 | ISS-751
JACINTOREQ-6268 | ISS-422,ISS-197,ISS-196 | ISS-103 | ISS-83 | Unit
JACINTOREQ-817 | ISS-422,ISS-197,ISS-196 | ISS-308 | ISS-292 | Unit
JACINTOREQ-1172 | ISS-318,ISS-208,ISS-203,ISS-204 | ISS-839 | ISS-1128
JACINTOREQ-6272 | ISS-318,ISS-208,ISS-203,ISS-306,ISS-204 | ISS-46 | ISS-1161,ISS-65 | Integration,Integration
JACINTOREQ-7468 | ISS-568,ISS-586 | ISS-208 | ISS-242
SITREQ-4992 | ISS-568,ISS-586 | ISS-13 | ISS-84 | Unit
JACINTOREQ-2354 | ISS-391,ISS-512 | ISS-79 | ISS-110 | Unit
JACINTOREQ-6208 | ISS-391 | ISS-197 | ISS-1163 | Integration
JACINTOREQ-6276 | ISS-391 | ISS-93 | ISS-112 | Unit
JACINTOREQ-7728 | ISS-585 | ISS-129 | ISS-111 | Unit
SITREQ-4553 | ISS-585 | ISS-377 | ISS-303,ISS-232,ISS-432 | Unit
JACINTOREQ-4941 | ISS-103 | ISS-835 | ISS-1129
JACINTOREQ-4600 | ISS-308 | ISS-827 | ISS-1126
JACINTOREQ-111 | ISS-46,ISS-13,ISS-6,ISS-14,ISS-7,ISS-5,ISS-47 | ISS-196 | ISS-215,ISS-1163 | Unit,Integration
JACINTOREQ-3497 | ISS-208 | ISS-793 | ISS-752,ISS-753,ISS-754,ISS-755,ISS-756,ISS-757,ISS-758,ISS-759
JACINTOREQ-3493 | ISS-79,ISS-12,ISS-11 | ISS-12 | ISS-112,ISS-90,ADASVISION-4390 | Unit,Integration,Unit
JACINTOREQ-430 | ISS-93,ISS-94,ISS-415 | ISS-414 | ISS-296 | Unit
JACINTOREQ-2891 | ISS-129,ISS-211 | ISS-803 | ISS-804
JACINTOREQ-3056 | ISS-129 | ISS-643 | ISS-759
JACINTOREQ-516 | ISS-129 | ISS-252 | ISS-112,ISS-65 | Unit,Integration
JACINTOREQ-601 | ISS-129,ISS-211 | ISS-378 | ISS-301 | Unit
JACINTOREQ-6203 | ISS-793 | ISS-309 | ISS-294 | Unit
SITREQ-396 | ISS-793 | ISS-417 | ISS-296 | Unit
SITREQ-403 | ISS-793 | ISS-6 | ISS-188,ISS-298,ISS-193,ISS-90 | Integration
SITREQ-447 | ISS-793 | ISS-641 | ISS-751,ISS-752,ISS-753,ISS-756,ISS-754,ISS-755
JACINTOREQ-61 | ISS-12,ISS-6,ISS-14,ISS-7 | ISS-413 | ISS-295,ISS-304,ISS-291 | Unit,Unit,Unit
JACINTOREQ-5396 | ISS-803 | ISS-236 | ISS-112 | Unit
JACINTOREQ-7790 | ISS-643 | ISS-159 | ISS-110 | Unit
SITREQ-5804 | ISS-643 | ISS-583 | ISS-740
JACINTOREQ-3496 | ISS-252 | ISS-1088 | ISS-1128,ISS-1126,ISS-1129
JACINTOREQ-587 | ISS-378 | ISS-203 | ISS-237
JACINTOREQ-6267 | ISS-378 | ISS-388 | ISS-816
JACINTOREQ-3282 | ISS-309 | ISS-45 | ISS-84,ISS-1161,ISS-65 | Unit,Integration,Integration
JACINTOREQ-856 | ISS-417 | ISS-375 | ISS-304,ISS-291,ISS-295 | Unit,Unit,Unit
JACINTOREQ-6216 | ISS-641 | ISS-512 | ISS-751
JACINTOREQ-7443 | ISS-641 | ISS-830 | ISS-1126
SITREQ-1548 | ISS-641 | ISS-9 | ISS-90 | Integration
JACINTOREQ-1368 | ISS-236 | ISS-214 | ISS-139,ISS-112 | Integration,Unit
JACINTOREQ-832 | ISS-159,ISS-177,ISS-178 | ISS-832 | ISS-1126
JACINTOREQ-7721 | ISS-583,ISS-587 | ISS-66 | ISS-112 | Unit
JACINTOREQ-8308 | ISS-583 | ISS-307 | ISS-301 | Unit
ISS-226 | ISS-203 | ISS-779 | ISS-752
JACINTOREQ-1050 | ISS-388 | ISS-745 | ISS-756
JACINTOREQ-2565 | ISS-388 | ISS-730 | ISS-751,ISS-752,ISS-753,ISS-756,ISS-754,ISS-755
JACINTOREQ-6213 | ISS-388 | ISS-306 | ISS-756
SITREQ-1451 | ISS-388 | ISS-177 | ISS-179
JACINTOREQ-1168 | ISS-214 | ISS-402 | ISS-297,ISS-300 | Unit,Unit
JACINTOREQ-3276 | ISS-307 | ISS-600 | ISS-753
JACINTOREQ-7600 | ISS-745 | ISS-399 | ISS-303 | Unit
JACINTOREQ-8280 | ISS-730 | ISS-158 | ISS-112 | Unit
SITREQ-5192 | ISS-730 | ISS-943 | ISS-1129
JACINTOREQ-847 | ISS-158,ISS-157 | ISS-157 | ISS-139 | Integration
JACINTOREQ-353 | ISS-77,ISS-126,ISS-127,ISS-100 | ISS-77 | ISS-111 | Unit
JACINTOREQ-3498 | ISS-152 | ISS-379 | ISS-300,ISS-297 | Unit,Unit
JACINTOREQ-827 | ISS-152,ISS-412 | ISS-62 | ISS-188,ISS-193,ISS-90 | Integration
JACINTOREQ-7580 | ISS-540 | ISS-152 | ISS-139,ISS-90,ISS-110,ISS-111 | Integration,Integration,Unit,Unit
JACINTOREQ-7524 | ISS-511 | ISS-540 | ISS-604
JACINTOREQ-1354 | ISS-217 | ISS-126 | ISS-112 | Unit
JACINTOREQ-5096 | ISS-217 | ISS-1064 | ISS-1128,ISS-1126,ISS-1129
JACINTOREQ-7943 | ISS-217 | ISS-511 | ISS-303 | Unit
JACINTOREQ-1871 | ISS-254 | ISS-217 | ISS-231,ISS-54 | Unit
JACINTOREQ-2865 | ISS-254 | ISS-14 | ISS-84,ISS-90 | Unit,Integration
JACINTOREQ-3232 | ISS-254 | ISS-254 | ISS-65,ISS-112 | Integration,Unit
JACINTOREQ-3500 | ISS-254 | ISS-418 | ISS-303,ISS-299 | Unit,Unit
JACINTOREQ-3501 | ISS-254 | ISS-204 | ISS-242
JACINTOREQ-1076 | ISS-213 | ISS-387 | ISS-294 | Unit
JACINTOREQ-957 | ISS-617 | ISS-840 | ISS-1128
JACINTOREQ-3499 | ISS-178 | ISS-7 | ISS-84,ISS-293,ISS-298 | Unit
JACINTOREQ-1499 | ISS-223 | ISS-946 | ISS-1128,ISS-1126,ISS-1129
JACINTOREQ-3294 | ISS-796 | ISS-419 | ISS-291 | Unit
JACINTOREQ-6217 | ISS-796 | ISS-386 | ISS-303 | Unit
SITREQ-1566 | ISS-796 | ISS-127 | ISS-112 | Unit
JACINTOREQ-723 | ISS-423 | ISS-213 | ISS-112 | Unit
JACINTOREQ-3494 | ISS-29 | ISS-60 | ISS-293,ISS-90 | Integration
JACINTOREQ-304 | ISS-27 | ISS-94 | ISS-112,ISS-90 | Unit,Integration
JACINTOREQ-3492 | ISS-8 | ISS-155 | ISS-110 | Unit
JACINTOREQ-8599 | ISS-794 | ISS-415 | ISS-296 | Unit
SITREQ-5805 | ISS-794 | ISS-394 | ISS-303 | Unit
JACINTOREQ-2924 | ISS-124 | ISS-59 | ISS-1161,ISS-65 | Integration,Integration
JACINTOREQ-396 | ISS-124 | ISS-833 | ISS-1126
JACINTOREQ-539 | ISS-803,ISS-124 | ISS-829 | ISS-1126
JACINTOREQ-3080 | ISS-645 | ISS-837 | ISS-1128,ISS-1126,ISS-1129
|  | ISS-395 | ISS-301 | Unit
|  | ISS-617 | ISS-756
|  | ISS-384 | ISS-296 | Unit
|  | ISS-382 | ISS-301 | Unit
|  | ISS-11 | ISS-90 | Integration
|  | ISS-389 | ISS-296 | Unit
|  | ISS-828 | ISS-1126
|  | ISS-834 | ISS-1126
|  | ISS-174 | ISS-112 | Unit
|  | ISS-178 | ISS-179
|  | ISS-570 | ISS-751,ISS-752
|  | ISS-398 | ISS-294 | Unit
|  | ISS-128 | ISS-139 | Integration
|  | ISS-211 | ISS-111 | Unit
|  | ISS-223 | ISS-112,ISS-90 | Unit,Integration
|  | ISS-5 | ISS-293,ISS-298
|  | ISS-796 | ISS-756
|  | ISS-412 | ISS-65 | Integration
|  | ISS-586 | ISS-751
|  | ISS-587 | ISS-90 | Integration
|  | ISS-423 | ISS-296 | Unit
|  | ISS-100 | ISS-111 | Unit
|  | ISS-376 | ISS-294 | Unit
|  | ISS-778 | ISS-751
|  | ISS-29 | ISS-167,ISS-168,ISS-169,ISS-170,ISS-171,ISS-172
|  | ISS-27 | ISS-137
|  | ISS-380 | ISS-301 | Unit
|  | ISS-381 | ISS-295,ISS-304,ISS-291 | Unit,Unit,Unit
|  | ISS-831 | ISS-1126
|  | ISS-133 | ISS-111 | Unit
|  | ISS-8 | ISS-90,ISS-123,ISS-65 | Integration,Unit,Integration
|  | ISS-794 | ISS-753
|  | ISS-420 | ISS-65 | Integration
|  | ISS-421 | ISS-303 | Unit
|  | ISS-47 | ISS-1161,ISS-65 | Integration,Integration
|  | ISS-124 | ISS-139 | Integration
|  | ISS-403 | ISS-295,ISS-304,ISS-291 | Unit,Unit,Unit
|  | ISS-645 | ISS-757,ISS-758
|  | ISS-401 | ISS-301 | Unit
|  | ISS-385 | ISS-303 | Unit

## Backward Traceability
SPS ID | MRD ID(s) | Test Case ID | Test Case Scope | SPS ID(s)
ISS-588 | JACINTOREQ-7469,SITREQ-4993 | ISS-215 | Unit | ISS-196
ISS-61 | JACINTOREQ-236 | ISS-65 | Integration | ISS-10,ISS-8,ISS-420,ISS-45,ISS-47,ISS-59,ISS-412,ISS-46,ISS-252,ISS-254
ISS-944 | JACINTOREQ-2887,JACINTOREQ-3160 | ISS-237 |  | ISS-203
ISS-817 | JACINTOREQ-592 | ISS-231 |  | ISS-217
ISS-392 | JACINTOREQ-310 | ISS-54 | Unit | ISS-217
ISS-731 | JACINTOREQ-8281 | ISS-804 |  | ISS-803
ISS-400 | JACINTOREQ-249 | ISS-295 | Unit | ISS-403,ISS-375,ISS-381,ISS-413
ISS-132 | JACINTOREQ-438 | ISS-164 | Unit | ISS-256
ISS-10 | JACINTOREQ-303,JACINTOREQ-56 | ISS-304 | Unit | ISS-403,ISS-375,ISS-413,ISS-381
ISS-777 | JACINTOREQ-1049,JACINTOREQ-7520 | ISS-167 |  | SITSW-695
ISS-80 | JACINTOREQ-407 | ISS-168 |  | SITSW-695
ISS-836 | JACINTOREQ-2887,JACINTOREQ-3160 | ISS-193 |  | ISS-6,ISS-62
ISS-841 | JACINTOREQ-2886,JACINTOREQ-3216 | ISS-169 |  | SITSW-695
ISS-416 | JACINTOREQ-528,SITREQ-633 | ISS-1126 |  | PDK-6486,ISS-827,ISS-831,ISS-833,ISS-830,ISS-944,ISS-1064,ISS-828,ISS-832,ISS-946,ISS-834,ISS-836,ISS-829,ISS-1088
ISS-422 | JACINTOREQ-524,JACINTOREQ-6268,JACINTOREQ-817,SITREQ-633 | ADASVISION-4390 | Unit | ISS-12
ISS-318 | JACINTOREQ-1172,JACINTOREQ-6272 | ISS-170 |  | ISS-29
ISS-838 | JACINTOREQ-2886,JACINTOREQ-3216 | ISS-751 |  | PDK-15233,ISS-730,ISS-512,ISS-585,ISS-778,ISS-570,ISS-586,ISS-568
ISS-568 | JACINTOREQ-7468,SITREQ-4992 | ISS-1128 |  | ISS-841,ISS-840,ISS-837,ISS-944,ISS-1064,ISS-946,ISS-1088,ISS-839,ISS-838
ISS-391 | JACINTOREQ-2354,JACINTOREQ-6208,JACINTOREQ-6276 | ISS-753 |  | PDK-15180,ISS-730,ISS-794,ISS-588,ISS-600,ISS-793
ISS-585 | JACINTOREQ-7728,SITREQ-4553 | ISS-1129 |  | ISS-835,ISS-836,ISS-837,ISS-1064,ISS-944,ISS-946,ISS-1088,ISS-943
ISS-103 | JACINTOREQ-4941 | ISS-300 | Unit | ISS-402,ISS-379,ISS-392
ISS-308 | JACINTOREQ-4600 | ISS-297 | Unit | ISS-402,ISS-379,ISS-392
ISS-839 | JACINTOREQ-2886,JACINTOREQ-3216 | ISS-757 |  | PDK-15234,ISS-731,ISS-793
ISS-46 | JACINTOREQ-111 | ISS-758 |  | PDK-15234,ISS-731,ISS-793
ISS-208 | JACINTOREQ-1172,JACINTOREQ-3497,JACINTOREQ-6272 | ISS-296 | Unit | ISS-384,ISS-400,ISS-389,ISS-423,ISS-414,ISS-415,ISS-417
ISS-13 | JACINTOREQ-111 | ISS-752 |  | PDK-15180,ISS-730,ISS-793,ISS-391,ISS-777,ISS-779,ISS-570
ISS-79 | JACINTOREQ-3493,JACINTOREQ-407 | ISS-291 | Unit | ISS-375,ISS-403,ISS-381,ISS-416,ISS-413,ISS-419
ISS-197 | JACINTOREQ-6268,JACINTOREQ-817 | ISS-303 | Unit | ISS-399,ISS-385,ISS-418,ISS-394,ISS-422,ISS-386,ISS-421,ISS-318,ISS-377,ISS-511
ISS-93 | JACINTOREQ-430 | ISS-754 |  | PDK-15233,ISS-641,ISS-793
ISS-129 | JACINTOREQ-2891,JACINTOREQ-3056,JACINTOREQ-516,JACINTOREQ-601 | ISS-232 |  | ISS-202
ISS-377 | JACINTOREQ-528 | ISS-432 |  | ISS-377
ISS-835 | JACINTOREQ-2887,JACINTOREQ-3160 | ISS-759 |  | ISS-793,ISS-643
ISS-827 | JACINTOREQ-2887,JACINTOREQ-3160 | ISS-301 | Unit | ISS-401,ISS-395,ISS-382,ISS-380,ISS-307,ISS-378
ISS-196 | JACINTOREQ-6268,JACINTOREQ-817 | ISS-294 | Unit | ISS-398,ISS-376,ISS-387,ISS-309
ISS-793 | JACINTOREQ-6203,SITREQ-396,SITREQ-403,SITREQ-447 | ISS-112 | Unit | ISS-43,ISS-93,ISS-12,ISS-66,ISS-158,ISS-223,ISS-214,ISS-213,ISS-236,ISS-127,ISS-174,ISS-126,ISS-254,ISS-252
ISS-12 | JACINTOREQ-303,JACINTOREQ-3493,JACINTOREQ-56,JACINTOREQ-61 | ISS-816 |  | ISS-817,ISS-388
ISS-414 | JACINTOREQ-310,SITREQ-633 | ISS-299 | Unit | ISS-418
ISS-803 | JACINTOREQ-5396 | ISS-172 |  | ISS-29
ISS-643 | JACINTOREQ-7790,SITREQ-5804 | ISS-139 | Integration | ISS-124,ISS-128,ISS-157,ISS-152,ISS-214
ISS-252 | JACINTOREQ-3496 | ISS-110 | Unit | ISS-80,ISS-79,ISS-152,ISS-155,ISS-159
ISS-378 | JACINTOREQ-587,JACINTOREQ-6267 | ISS-83 | Unit | ISS-103
ISS-309 | JACINTOREQ-3282 | ISS-84 | Unit | ISS-45,ISS-7,ISS-14,ISS-13
ISS-417 | JACINTOREQ-856,SITREQ-633 | ISS-111 | Unit | ISS-77,ISS-100,ISS-152,ISS-133,ISS-211,ISS-129
ISS-6 | JACINTOREQ-111,JACINTOREQ-61 | ISS-293 |  | ISS-7,ISS-60,ISS-5
ISS-641 | JACINTOREQ-6216,JACINTOREQ-7443,SITREQ-1548 | ISS-188 |  | ISS-62,ISS-6
ISS-413 | JACINTOREQ-310,SITREQ-633 | ISS-740 |  | ISS-583
ISS-236 | JACINTOREQ-1368 | ISS-90 | Integration | ISS-9,ISS-8,ISS-94,ISS-11,ISS-12,ISS-14,ISS-152,ISS-223,ISS-60,ISS-6,ISS-62,ISS-61,ISS-587
ISS-159 | JACINTOREQ-832 | ISS-137 |  | ISS-40
ISS-583 | JACINTOREQ-7721,JACINTOREQ-8308 | ISS-298 |  | ISS-6,ISS-5,ISS-7
ISS-1088 | JACINTOREQ-2886,JACINTOREQ-2887,JACINTOREQ-3160,JACINTOREQ-3216 | ISS-604 |  | ISS-540
ISS-203 | ISS-226,JACINTOREQ-1172,JACINTOREQ-6272 | ISS-242 |  | ISS-208,ISS-204
ISS-388 | JACINTOREQ-1050,JACINTOREQ-2565,JACINTOREQ-6213,SITREQ-1451 | ISS-123 | Unit | ISS-8
ISS-45 | JACINTOREQ-236 | ISS-755 |  | ISS-641,ISS-730,ISS-793
ISS-375 | JACINTOREQ-249 | ISS-171 |  | SITSW-695
ISS-512 | JACINTOREQ-2354 | ISS-1161 | Integration | ISS-59,ISS-45,ISS-47,ISS-10,ISS-46
ISS-830 | JACINTOREQ-2887,JACINTOREQ-3160 | ISS-292 | Unit | ISS-308
ISS-9 | JACINTOREQ-303,JACINTOREQ-56 | ISS-1162 | Integration | ISS-10
ISS-214 | JACINTOREQ-1168 | ISS-1163 | Integration | ISS-196,ISS-197
ISS-832 | JACINTOREQ-2887,JACINTOREQ-3160 | ISS-756 |  | SITSW-5775,ISS-730,ISS-745,ISS-617,ISS-796,ISS-306,ISS-793
ISS-66 | JACINTOREQ-236 | ISS-179 |  | ISS-178,ISS-177
ISS-307 | JACINTOREQ-3276
ISS-779 | JACINTOREQ-1049
ISS-745 | JACINTOREQ-7600
ISS-730 | JACINTOREQ-8280,SITREQ-5192
ISS-306 | JACINTOREQ-6272
ISS-177 | JACINTOREQ-832
ISS-402 | JACINTOREQ-249
ISS-600 | JACINTOREQ-7469,SITREQ-4993
ISS-399 | JACINTOREQ-249
ISS-158 | JACINTOREQ-847
ISS-943 | JACINTOREQ-2887,JACINTOREQ-3160
ISS-157 | JACINTOREQ-847
ISS-77 | JACINTOREQ-353
ISS-379 | JACINTOREQ-249
ISS-62 | JACINTOREQ-236
ISS-152 | JACINTOREQ-3498,JACINTOREQ-827
ISS-540 | JACINTOREQ-7580
ISS-126 | JACINTOREQ-353
ISS-1064 | JACINTOREQ-2886,JACINTOREQ-2887,JACINTOREQ-3160,JACINTOREQ-3216
ISS-511 | JACINTOREQ-7524
ISS-217 | JACINTOREQ-1354,JACINTOREQ-5096,JACINTOREQ-7943
ISS-14 | JACINTOREQ-111,JACINTOREQ-61
ISS-254 | JACINTOREQ-1871,JACINTOREQ-2865,JACINTOREQ-3232,JACINTOREQ-3500,JACINTOREQ-3501
ISS-418 | JACINTOREQ-310,SITREQ-633
ISS-204 | JACINTOREQ-1172,JACINTOREQ-6272
ISS-387 | JACINTOREQ-310
ISS-840 | JACINTOREQ-2886,JACINTOREQ-3216
ISS-7 | JACINTOREQ-111,JACINTOREQ-61
ISS-946 | JACINTOREQ-2887,JACINTOREQ-3160
ISS-419 | JACINTOREQ-528,SITREQ-633
ISS-386 | JACINTOREQ-528
ISS-127 | JACINTOREQ-353,JACINTOREQ-438
ISS-213 | JACINTOREQ-1076
ISS-60 | JACINTOREQ-236
ISS-94 | JACINTOREQ-430
ISS-155 | JACINTOREQ-438
ISS-415 | JACINTOREQ-430,SITREQ-633
ISS-394 | JACINTOREQ-528
ISS-59 | JACINTOREQ-236
ISS-833 | JACINTOREQ-2887,JACINTOREQ-3160
ISS-829 | JACINTOREQ-2887,JACINTOREQ-3160
ISS-837 | JACINTOREQ-2887,JACINTOREQ-3160
ISS-395 | JACINTOREQ-249
ISS-617 | JACINTOREQ-957
ISS-384 | JACINTOREQ-249
ISS-382 | JACINTOREQ-310
ISS-11 | JACINTOREQ-303,JACINTOREQ-3493,JACINTOREQ-56
ISS-389 | JACINTOREQ-249
ISS-828 | JACINTOREQ-2887,JACINTOREQ-3160
ISS-834 | JACINTOREQ-2887,JACINTOREQ-3160
ISS-174 | JACINTOREQ-438
ISS-178 | JACINTOREQ-3499,JACINTOREQ-832
ISS-570 | JACINTOREQ-1049
ISS-398 | JACINTOREQ-249
ISS-128 | JACINTOREQ-56
ISS-211 | JACINTOREQ-2891,JACINTOREQ-601
ISS-223 | JACINTOREQ-1499
ISS-5 | JACINTOREQ-111
ISS-796 | JACINTOREQ-3294,JACINTOREQ-6217,SITREQ-1566
ISS-412 | JACINTOREQ-827,SITREQ-633
ISS-586 | JACINTOREQ-7468,SITREQ-4992
ISS-587 | JACINTOREQ-7721
ISS-423 | JACINTOREQ-723,SITREQ-633
ISS-100 | JACINTOREQ-353
ISS-376 | JACINTOREQ-249
ISS-778 | JACINTOREQ-1049
ISS-29 | JACINTOREQ-3494,JACINTOREQ-438
ISS-27 | JACINTOREQ-304
ISS-380 | JACINTOREQ-249
ISS-381 | JACINTOREQ-528
ISS-831 | JACINTOREQ-2887,JACINTOREQ-3160
ISS-133 | JACINTOREQ-438
ISS-8 | JACINTOREQ-303,JACINTOREQ-3492,JACINTOREQ-56
ISS-794 | JACINTOREQ-8599,SITREQ-5805
ISS-420 | JACINTOREQ-236,SITREQ-633
ISS-421 | JACINTOREQ-438,SITREQ-633
ISS-47 | JACINTOREQ-111
ISS-124 | JACINTOREQ-2924,JACINTOREQ-396,JACINTOREQ-539,JACINTOREQ-56
ISS-403 | JACINTOREQ-249
ISS-645 | JACINTOREQ-3080
ISS-401 | JACINTOREQ-249
ISS-385 | JACINTOREQ-249

## Traceability Deviations
Coverage Type | Parameter ID(s) | Justification for Traceability Deviation
Missing Test Case | ISS-1157 | This test case is resolving the functional requirement of VHWA. PDK-7833, PDK-7832 are the FRs of VHWA. This test case is tested out from vision_apps through custom configurations.

## Template Revision History
Author | Version | Date | Description
Krishna/ Dhruv | A | 20/1/2023 | Initial version